## MAIN
Project: Point Cloud Processing - Extracting Railway Track Geometry
| Project Manager |  | Desired tools to use during the Project |  |  |  |  | Why I have selected this Project?
| Viktor Lindberg |  | Python |  |  |  |  | In the previous course (D7015B) we analysed abnormal events from track vibration data. The model could say that something was wrong at a location, but not what was wrong. A point cloud gives the actual shape of the track, so I wanted to see if the geometry at those same spots can explain the events, or give more information around it.
| Supervisor: Amit Patwardhan |  | NumPy / pandas
Open3D
| Start Date |  | scikit-learn
| 2026-09-08 |  | laspy / PDAL
GitHub
| End Date |  | ChatGPT / Claude for coding assistance
| 2026-10-30 |  | CloudCompare (new tool outside vs to visualize dataset)
|  | Milestone | Project title
|  | Reached Milestone in time | Extract the railway track geometry from point cloud data, and compare it with the abnormal vibration events from the previous course.
Delayed
|  | Task Name | Status | Duration [d] | Start Date | End Date | NOTE | Main Goals
| 1 | 1.1 Agree project idea and scope with supervisor | 100% | 3 | 2026-09-07 | 2026-09-09 |  | Understand what the common track geometry faults are, agree the scope with Amit, and have the tools and a test point cloud ready so the work can start as soon as the LTU data arrives. --> Done but with new dataset --> Meeting set on 2026-06-24
|  | 1.2 Submit Project Time Plan | 100% | 2 | 2026-09-09 | 2026-09-10
|  | 1.3 Set up tools and GitHub repo - Python, Open3D, laspy, CloudCompare | 100% | 7 | 2026-09-11 | 2026-09-17
|  | 1.4 Read report from Amit: Sharma et al. (2018) - track geometry faults (gage, cross-level, cant, surface, twist) and TQI | 100% | 4 | 2026-09-14 | 2026-09-17
|  | 1.6 Write Report 1 - Introduction | 100% | 4 | 2026-09-15 | 2026-09-18
|  | 1.7 Follow up with Amit on receiving data | 100% | 3 | 2026-09-16 | 2026-09-18
| 2 | 2.1 Demonstration 1 + hand in Report 1 (Introduction) | 100% | 1 | 2026-09-18 | 2026-09-18 | Data needed could not be fetched. Timeplan is adjusted for and project adapted to data availability | Get from a raw point cloud to the two extracted rails and a fitted track centreline, and divide the track into fixed sections. ---> Look into Catmul-rom.
|  | 2.2 Load and clean a point cloud - crop a test section, downsample, remove outliers | 100% | 3 | 2026-09-21 | 2026-09-23
|  | 2.3 Research about Catmul-rom and update report | 100% | 5 | 2026-09-24 | 2026-09-28 | <From hereon new project>
|  | 2.4 Load data and first attempt at analyzing it | 100% | 3 | 2026-09-29 | 2026-10-01
|  | 2.5 Write Report 2 - Method | 0% | 7 | 2026-09-29 | 2026-10-05
| 3 | 3.1 Demonstration 2 + hand in Report 2 (Introduction + Method) | 0% | 1 | 2026-10-05 | 2026-10-05 |  | Measure the geometry of every section and turn the point cloud into a condition table with one row per section, including a track quality index.
|  | 3.2 Clean the data and noise points | 0% | 6 | 2026-10-05 | 2026-10-10
|  | 3.3 Create repeatable catmul-rom algorithm | 0% | 4 | 2026-10-11 | 2026-10-14
|  | 3.4 Visualise this in a 3D environment - should be possible to analyze change over time using catmul-rom | 0% | 3 | 2026-10-13 | 2026-10-15
|  | 3.5 Write Report 3 - Results | 0% | 4 | 2026-10-13 | 2026-10-16
| 4 | 4.1 Demonstration 3 + hand in Report 3 (Introduction + Method + Results) | 0% | 1 | 2026-10-16 | 2026-10-16 |  | Place the vibration events from the previous course on the same track positions, and see whether the extracted geometry says anything about why those events happened.
|  | 4.2 Simulate over mutiple runs | 0% | 4 | 2026-10-19 | 2026-10-22
|  | 4.3 Analyze change over time | 0% | 3 | 2026-10-21 | 2026-10-23
|  | 4.4 Explorative study - suggest how future studies could build upon this and these findings | 0% | 5 | 2026-10-22 | 2026-10-26
|  | 4.5 Clean and comment the code, write the README | 0% | 4 | 2026-10-23 | 2026-10-26
|  | 4.6 Prepare Final Demonstration | 0% | 2 | 2026-10-26 | 2026-10-27
| 5 | 5.1 Final Demonstration | 0% | 1 | 2026-10-28 | 2026-10-28 |  | Show the full pipeline live - from raw point cloud to condition table and the comparison with the vibration data.
| 6 | 6.1 Draft discussion and conclusions | 0% | 7 | 2026-10-20 | 2026-10-26 |  | Deliver the complete report in the D7016B template and hand in all code on CANVAS.
|  | 6.2 Assemble the full report in the D7016B template | 0% | 3 | 2026-10-26 | 2026-10-28
|  | 6.3 Hand in Final project Report (complete) | 0% | 1 | 2026-10-28 | 2026-10-28
|  | 6.4 Submit all code on CANVAS | 0% | 2 | 2026-10-29 | 2026-10-30
Optional Tasks (if time is left):
Run the pipeline on a second track section to see if it generalises
Apply further analysis to any correleation between abnomalies and track behaviour